## Sheet1
Defect_ID | Title | Status | Severity | Assigned_To | Module | Days_Open | Target_Date | Comments
DEF-001 | Login page crashes on Safari | Open | Critical | John S | Auth | 3 | 2026-03-01 | Reproduced on Safari 16+
DEF-002 | Payment gateway timeout after 30s | Open | Blocker | Priya M | Payments | 7 | 2026-02-28 | Blocking all payment processing
DEF-003 | Report export fails for large datasets | In Progress | High | Unassigned | Reports | 2 | 2026-03-05 | Memory issue suspected
DEF-004 | User session expires too early | Open | Medium | Carlos R | Auth | 5 | 2026-03-10 | Timeout set to 15min but expires at 5min
DEF-005 | Email notifications not sending | Blocked | Blocker | John S | Notifications | 12 | 2026-02-25 | SMTP config needs review - blocking QA
DEF-006 | Dashboard charts not loading on mobile | In Progress | High | Priya M | Dashboard | 4 | 2026-03-03 | Chart.js version conflict
DEF-007 | Password reset link invalid after 1 use | Open | Critical | Carlos R | Auth | 1 | 2026-03-07 | Token invalidation bug
DEF-008 | Search results return wrong data | Blocked | Blocker | Unassigned | Search | 9 | 2026-03-01 | Blocking UAT sign-off
DEF-009 | PDF export missing header logo | Open | Low | John S | Reports | 6 | 2026-03-15 | Minor cosmetic issue
DEF-010 | API rate limit not enforced correctly | In Progress | High | Priya M | API | 3 | 2026-03-04 | Security concern - needs urgent fix